## Weekly Plan
Week | Phase | Title | Goal | Backend - Key Tasks | Flutter - Key Tasks | Deliverable / Demo | Dependencies / Risks | Status | Progress %
week 1 | Phase 1 | Identity & Authentication User Profile Management KYC - Aadhaar Flow | Mobile OTP-based login system Basic user profile CRUD Complete Aadhaar verification pipeline | Custom AppUser model, OTP generation & verification, JWT token endpoints, User registration MeSerializer, MeUpdateSerializer, Profile endpoints AadhaarKycStartView, AadhaarKycSubmitOtpView, Surepass integration, OTP cooldown logic | Mobile number input screen, OTP verification screen, Token storage, Auto token refresh Profile screen, Edit profile functionality Aadhaar number input, OTP screen, Cooldown UI | Operator can login via mobile OTP and receive JWT tokens Operator can view and update their profile Operator can verify via Aadhaar OTP | SMS gateway integration (using console print), OTP expiry handling | COMPLETED | 100%
Week 2 | Phase 2 | KYC - Details Verification KYC - DL Flow KYC - Face Verification | Match user details with eKYC data Driving License verification Face liveness + face match | AadhaarKycVerifyDetailsView, Name/DOB/Gender matching logic DLKycStartView, DLKycVerifyDetailsView, Surepass DL API FaceLivenessView, FaceMatchView, Surepass face APIs, Photo storage | Verify details screen with pre-filled data DL number + DOB input, Verify details screen Liveness screen, Face match screen, Camera integration | Operator details match eKYC data Operator can verify via Driving License Operator completes face verification and reaches verified state | Name normalization edge cases DL API reliability Camera permissions, Image quality, Bandwidth | COMPLETED | 100%
Week 3 | Phase 3 | Attendance v1 (Check-In/Out + Geo) | Track operator presence at center with GPS validation | • Create attendance app: CheckIn + CheckOut models • Geo-fencing: haversine distance; default radius 200m configurable per center • Time validation windows; return error with distance if outside • APIs: check-in/out; my-history; admin live + summary views • Background jobs: auto-checkout; attendance stats | • Check-in UI: location permission, GPS capture, show distance, submit + feedback • Optional selfie for audit • Check-out UI with total duty hours + notes • Attendance history list • Offline-friendly queue + retry + pending indicator | Demo: Operator checks in within 200m → success; too far → friendly error Admin dashboard shows live attendance (checked-in / total) | • GPS accuracy variance • Location permission UX (Android 12+) • Offline networks at centers • Device time skew (server vs device) • Battery drain from GPS usage | in progress | 25%
Week 4 | Phase 3 | Incident / Support v1 + Media Upload | Allow operators to report issues at center with photo evidence | • Create incidents app: Incident + IncidentAttachment models • Multipart upload endpoint (size/type validation); store media under incidents/{id}/ • APIs: operator report + my-reports; admin list + status updates + dashboard summary • Optional notifications for critical incidents / resolution updates | • Raise incident screen: category, severity, title/description, attach photo, preview • My incidents list + filters + status badge • Incident detail screen with attachments + status timeline | Demo: Operator reports "Internet down" with photo → admin sees dashboard → resolves → operator sees resolution | • Storage decision (S3 vs local; S3 recommended production) • Upload time for large files • Network reliability • Image compression requirement | in pipline | 0%
Week 5 | Phase 3 | Reporting + Exports + Operational Dashboards | Provide insights and data exports for management | • Reports endpoints: assignments, attendance, incidents, operator performance • CSV export endpoints for reports (handle large datasets safely) • Dashboard aggregations: overview + exam-specific • Performance optimizations: indexes, select_related/prefetch_related, caching | • Simple dashboard tiles: duties count, attendance rate, incidents count • Optional basic charts (last 7 days trends) • Keep heavy reporting/export on web/admin panel | Demo: Dashboard shows today's status; export attendance CSV and analyze in Excel | • Query performance for large datasets (10k+ assignments) • Permission leakage across clients • CSV file size/memory usage • Real-time updates (websockets optional later) | in pipline | 0%
Week 6 | Phase 3 | Hardening: RBAC, Security, Throttling, Cleanup | Secure the system and clean up sensitive data | • RBAC permissions: IsInternalAdmin, IsClientAdmin, IsOperator, etc. • Client scoping on all queries; endpoint protection review • Rate limiting: OTP, KYC, check-in (idempotent) • Management commands: cleanup expired KYC/OTP sessions; sensitive field clearing • Security headers, CORS tightening, HTTPS settings, audit logging (optional) | • Logout on 401; token refresh failure handling • User-friendly error screens + retry patterns • Secure storage hygiene (no sensitive logs) | Demo: client isolation (403), throttling messages, cleanup commands run, endpoint audit pass | • Policy decisions on retention • Vendor/legal constraints (Aadhaar retention rules) • Perf impact of scoping filters | in pipline | 0%
Week 7 | Phase 3 | Performance + Reliability | Optimize for scale and handle edge cases | • Load testing with locust/JMeter on key endpoints • DB indexes + query optimization (avoid N+1; only/defer for large fields) • Caching for master + exam data; TTL tuning • Background jobs (celery/redis optional) for heavy tasks • Better error logging (Sentry), retries for external APIs | • Performance: lazy loading, image upload progress, caching • Crash hardening: null safety, camera failures, low memory • Optional analytics for key events | Demo: load test results (100 concurrent); perf before/after; app memory improvements | • Emulator vs real device differences • Infrastructure scaling constraints • Third-party API reliability | in pipline | 0%
Week 8 | Phase 3 | UAT & Bug-Fix Sprint | End-to-end testing and bug fixes | • UAT scenarios + automated tests for critical flows • Manual test checklist + regression tests • Bug fixes discovered in UAT | • UAT build; device coverage (Android 10–13+) • UI polish + loading states • Routing state machine stabilization | Demo: full UAT walkthrough, checklist sign-off, critical bugs fixed | • Stakeholder feedback changes scope • Time pressure; defer non-critical bugs • Device-specific issues | in pipline | 0%
Week 9 | Phase 3 | Release Prep (Deployment + Monitoring) | Production deployment and monitoring setup | • uWSGI config; Nginx reverse proxy; SSL; static/media serving • Production settings: DEBUG off, ALLOWED_HOSTS, secrets via env • Logging + monitoring: health checks, Sentry, metrics (optional Prometheus/Grafana) • Backup/restore + DR plan; staging → production rollout plan | • Release build signing; versioning; AAB for Play Store • Crash reporting (Crashlytics/Sentry) + test • Store listing prep (screenshots, privacy policy) | Demo: staging deploy successful, monitoring dashboards, release checklist complete, rollout plan approved | • Infrastructure access & secrets management • SSL cert setup • App store review timelines | in pipline | 0%
10 | Performance + reliability | • Load test key APIs (OTP, list assignments, check-in) • Add DB indexes and optimize queries • Add caching where safe • Background jobs (optional) for heavy tasks | • App performance polish (images upload progress) • Reduce crashes, handle low memory • Analytics logging (optional) | Demo: basic load test results + before/after improvements. | Emulator vs real device differences; infrastructure later. | Planned | 0%
11 | UAT & bug-fix sprint | • End-to-end UAT scenarios + test scripts • Fix edge cases (reinstall, network drop, retries) • Regression tests for auth/KYC/attendance | • UAT build + UI polish • Fix UX rough edges • Stabilize navigation state machine | Demo: full UAT walk-through; checklist signed off. | Stakeholder feedback may shift scope; time pressure. | Planned | 0%
12 | Release prep (deployment + monitoring) – after dev | • uWSGI config + production settings • Nginx + static/media serving • Logging/monitoring basics • Backup/restore plan • Rollout plan and runbooks | • Release build signing • Versioning + update strategy • Crash reporting (optional) | Demo: staging deployment, release checklist, rollout plan. | Infra access, secrets management, certs, app store process. | Planned | 0%

## Milestones
Milestone | Target Week | Definition of Done | Owner(s)
Onboarding + KYC stable (resume-safe) | 2 | OTP login + profile + Aadhaar OTP + liveness + face match reliably reaches Home; reinstall resume works. | Backend + Flutter
Master data ready (Client/Centers) | 3 | Create/list centers with client scoping + bulk import; admin permissions tested. | Backend
Scheduling ready (Exam/Shift/Allocations) | 4 | Exams + shifts + center allocations CRUD + validations; basic views. | Backend
Assignments v1 live | 5 | Operators can see duties; admin can bulk assign; confirm flow works. | Backend + Flutter
Attendance v1 live | 6 | Check-in/out works with geo; admin live counts. | Backend + Flutter
Incident reporting v1 | 7 | Operator can raise incident with optional photo; admin triage. | Backend + Flutter
Reporting + exports | 8 | Manager can pull CSVs for assignments/attendance/incidents; queries optimized. | Backend
Security hardening | 9 | RBAC, throttling, cleanup commands, audit logs. | Backend
UAT signoff | 11 | End-to-end test checklist passed; critical bugs closed. | Backend + Flutter
Release ready | 12 | uWSGI + nginx + deployment runbook + app release build. | Backend + Flutter/DevOps